## Sheet1
Activity Name | Type | Week | Responsible | Estimated Hours | Actual Hours | Status | Comments
Week 10
Bug fixes | Development | 10 | Jedd, Gregg | 3 | 2 | Done
Manager GUI | Development | 10 | Jedd, Ob | 5 |  | In Progress | Unable to finish :-(
Design Document | Planning | 10 | Rich | 1 | 1 | In Progress | Updated UML as of 11 PM Monday. Not sure if OB's code is in yet.
Modify/Cancel orders | Development | 10 | Jedd/Johanna | 1 | 1 | Done | The function is working with the remove button in the GUI
Requirements Documents | Planning | 10 | Johanna | 1 | 0.3 | Done | Modify use cases and use case diagram as requested. Adjust to R2 requirements
JUnit Tests | Testing | 10 | Jenny | 2 | 1 | Done
R2 Presentation | Planning | 10 | Johanna, Richard | 0.3 | 0.3 | Done | Create Powerpoint presentation
Week 9
JUnit Tests | Testing | 9 | Jenny | 2 | 1 | Done
Acceptance Test Plan | Testing | 9 | Jenny, Johanna | 1 | 5 | Done | Rewrote the entirety of the acceptance test plan
Week 8
JUnit Tests | Testing | 8 | Jenny | 3 | 2 | In Progress | Completed some more Junit tests
Cross Team Testing | Testing | 8 | All | 4 | 3 | Done
Database read/writing | Development | 8 | Rich | 3 | 2 | Done | Everything tested correctly on the first try. It was one of those beautiful moments in coding that every programmer cherishes.
More GUI work | Development | 8 | Jedd | 2 | 2 | In Progress | GUI feature complete for R1 features. Still some bugs and things that need to be fixed however.
Week 7
Order Time Estimation | Development | 7 | Gregg | 3 | 2 | In Progress | Almost finished, just need to test it
GUI | Development | 7 | Jedd | 5 | 5 | In Progress | Almost finished the employee screens. Just need to ensure that cancellation works. Then, all that is left to do is the manager view.
DeliveryManager (code inspection) | Development | 7 | Rich | 1 | 1 | Done
File read/writing | Development | 7 | Rich |  |  | In Progress
Modify/Cancel orders | Development | 7 | Johanna | 1 | 1 | In Progress
JUnit Tests | Testing | 7 | Jenny | ? |  | In Progress | More tests are needed to reflect new functionality.
Manager report | Development | 7 | obaseki | 3 | ? | In Progress | Almost done, just need to send manager report to text file and make sure it updates
Week 6
Release 2 planning and assignments | Planning | 6 | All | 1 | 1 | Done | Created a list of things to do for release 2, and assigned coding parts to each team member
GUI | Development | 6 | Jedd | 5 | 1.5 | In progress | Created the Welcome, phone operator, and user information input screens. Still have the manager and order related screens to do.
Order data/customer preferences | Development | 6 | Jenny | 1 | 1 | Done | Can access customer's last order.
Modify/Cancel orders | Development | 6 | Johanna | 1 | 1 | in porgress | create the cancel order, need to test and work on modify order
Week 5
Test Planning Document | Planning | 5 | Jenny | 5 | 4 | Done | Updated based on feedback and Release 1 outcome.
Design Document | Development/Design | 5 | Jedd | 3 | 2.5 | Done | Updated to reflect feedback and changes made in Release 1.
Requirements Document | Requirements | 5 | Johanna | 3 | 3 | Done | Updated to reflect feedback and changes made in Release 1.
JUnit Tests | Testing | 5 | All | 5 | 5 | Done | Created test cases for all necessary classes.
Integration | Development/Testing | 5 | All | 4 | 3 | Done
Command-Line Interface (CLI) | Development | 5 | Jedd, Ob | 5 | 5 | Done | Interface to run program using the command line.
Menu and Configuration Parsing | Development/Design | 5 | Jedd | 2 | 1.5 | Done | Can now read the file formats we had defined!
Delivery Management Class | Development/Design | 5 | Rich | 3 | 2 | Done | There may possibly be a threading bug in there... But I think it's fixed.
Read-Me.txt, tagging, .jar file |  | 5 | Jedd | 1 | 1 | Done | Created read-me file with instructions, bugs, etc. Tagged all files as Release 1. Created executable .jar file.
Week 4
Test planning document | Planning | 4 | All | 4 | 1.5 | Done
Test planning document | Planning | 4 | Jenny | 4 | 4 | Done
Design document | Development/Design | 4 | Ob and Richard | 2 | 2 | Done
Delivery class | Development | 4 | Richard |  | 1 | Done | Updated to work with the time system; only part left is the report system
Phone Operator class | Development | 4 | Johanna |  | 1.5 | Done | Delivery and order classes updated to use enums for the destination
Kitchen and WorkQueue classes | Development | 4 | Jedd and Gregg | 3 | 4 | Done
Oven Class | Development | 4 | Gregg | 3 | 3 | Done
Chef class | Development | 4 | Jedd | 1 | 0.33 | Done
Week 3
Food class | Development | 3 | Jenny |  | 3 | Done | Will do more work for it later; I have 3 midterms.
Time system code | Development | 3 | Jedd |  | 0.5 | Done
Order class | Development | 3 | OB |  | 3 | Done | Was revised with design
Order class and supporting code | Development | 3 | Jedd |  | 1 | Done
Oven class design | Development | 3 | Gregg |  | 1 | Done | Need to discuss design with team members before I finish coding.
Order class design | Development | 3 | All |  | 4 | Done
Delivery Class design/basic code | Development | 3 | Richard |  | 1 | Done | Dependent on order class and time system; will be modified to suit them as they are finalized
phone operator class | development | 3 | Johanna |  | 2 | Done | need to do more work later.
Test plan document | Testing | 4 | Jenny | 2 |  | Done
Design document | Development/Design | 4 | Ob and Richard | 2 |  | Done
Overview kitchen and phone operator classes with group. | Development/Design | 4 | All | 0.5 |  | Done
Week 2
Requirements document |  | 2 | All |  | 2 | Done | Awesome team work
Project Plan |  | 2 | All |  | 1 | Done
UML Case Diagram |  | 2 |  |  | 1 | Done
Use Case Descriptions |  | 2 | All |  | 2 | Done
Development Tasks |  | 2 | All |  | 0.5 | Done
Time system | Development | 3 | Jedd |  |  | Done
Test plan document | Testing | 3 | Jenny |  |  | TODO
Design document | Development/Design | 3 | Ob and Richard |  |  | TODO
Food class | Development | 3 | Jenny |  |  | Partially completed
Phone operator | Development | 3 | Johanna |  |  | Partially completed
Order class | Development | 3 | Ob |  |  | Done
Oven class | Development | 3 | Gregg |  |  | TODO
Chef/Cook class | Development | 3 | Jedd |  |  | TODO
Delivery class | Development | 3 | Richard |  |  | Partially completed
Week 1
Google Docs setup | Preparation | 1 | All |  | 0.2
Discussed high level program requirements | Requirements | 1 | All |  | 1
Documented unanswered questions | Requirements | 1 | All |  | 1
Next meeting scheduled | Coordination | 1 | All
Document SVN workflow | Documentation | 2 | Jedd |  |  | Done
Investigate SVN Eclipse plugins | Preparation | 2 | Jedd |  |  | Done | There are two SVN plugins for Eclipse. Subclipse and Subversive. One is officially supported by the Eclipse foundation, the other is officially supported by the Subversion developers.